## Event Manaement Plan Timeline
EVENT MANAGEMENT PLAN TEMPLATE
EVENT / ACTIVITY | [Event Name] | [9 empty] | ORGANISATION |  |  |  |  | [Company name]
EVENT DATE | [Date/s] | [9 empty] | LOCATION |  |  |  |  | [Site Location & Address]
EVENT ORGANISER / MANAGER | [Contact Name & Phone]
TASK | MONTH - 12 MONTHS OUT | MONTH - 6 MONTHS OUT | MONTH - 5 MONTHS OUT | MONTH - 4 MONTHS OUT | MONTH - 3 MONTHS OUT | Date - 8 weeks out | Date - 7 weeks out | Date - 6 weeks out | Date - 5 weeks out | Date - 4 weeks out | Date - 3 weeks out | Date - 2 weeks out | Date - 1 week out | EVENT DAY - Date | POST EVENT | RESPONSIBLE (INTIALS) | COMPLETED | TASK NOTES
Venue/Site Planning
Book location/venue | X
Event Planning
Set event date | X
Complete Council application | X
Assign staff tasks | X
Lock in contractors | X
Advertising - Print, Website, Radio, Social Media
Create/update website for event
Review Media plan
Book event advertising
Advertising design
Program
Write program content
Design program poster layout
Approve program design
Print program poster
Entertainment
Draft line up
Final performer line up
Send performer confirmations
Short term services agreements for all performers
Create draft contact number listing
Entertainment - MC
Book MC
Write MC notes
Send notes
Sponsorship
review sponsorship prospectus
upload prospectus to website
Send out proposal pack via email
Follow up
Send confirmation/acknowledgement
Issue invoices upon receipt of confirmation
Stallholders
Review stallholder application form
Mail out form to previous stallholders - applications are now open
Review stallholder layout
Send confirmation to all stallholders
Send unsuccessful letters where necessary
Update website
Operations - Administration
Complete Council approval Application
Source ticketing platform
Notification to Police - NOI to hold public assembly
Notifcation to public authorities
Complete risk assessment
TMP to operations to assist with rostering staff
Staff rostering
Create parking list
Operations - Security & Safety
Discuss event with local Police
Book security
Develop security plan
Book first aid
Inclusive events - Quiet Session
Source ticketing platform
Book infrastructure
Book activities
Operations - Equipment Hire
Obtain quotes
Review quotes
Confirm suppliers and book infrastructure
Notify unsuccessful suppliers
Send bump information & site map for infrastructure locations
Carnival rides
Speak to contracted supplier and confirm date
Obtain insurances and Risk Assessment
Obtain site map for ride layout for Carnival area
Fireworks
Speak to contracted supplier and confirm date
Obtain insurances and Risk Assessment
Send notification to local Fire Brigade
Send notification letters to residents if event site is in a residential area
Budget
Develop budget
Update budget
Reconcile budget
General